ATR of 6th   IQAC Meeting 2019-20

| Plan | Action Taken |
| --- | --- |
| a) Organizing annual health day immediately after the admission. | Done |
| b) Organizing General and Departmental alumni meet. | Done |
| c) Publishing Departmental research journals. | Five of the departments have published. |
| d) Conducting Academic audit of the departments. | Done |
| e) Conducting administrative auditof the college. | To be done. The appointment of auditor is taken. |
| f) Organizing a workshop on Beauty Culture. | Done |
| g) Introduction of a modified version of management app. | To be done |
| h) Renovating the College Canteen. | Under renovation |
| i) Organizing some programmes on environmental awareness. | Done |
| k) Completing the herbarium. | To be done |
| l) Organizing short term programme on folk language teaching. | Done |
| m) Complete the rain water harvesting project. | Partially done. |
| n) Finalising the Green Audit of the old campus. | On process |
| o) To organize the International Yoga Day. | Done. |